## Procurement timetable
[14 empty] | Updated |  | 2019-05-20
2018-07-04
Procurement timetable - FUT
FUT procurement identification number (FUT id nr) | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project (Extension part) | Procurement procedure | Only prequalified suppliers in TransQ can participate | Contract type | Scheduled time for qualification of suppliers | Scheduled time for invitation to tender | Scheduled time for submission of tenders | Planned assignment start | Estimated cost SEK million | Link to further information | Procurement certainty | Procurement certainty | Comment
15014 | geodetic measurement | geodetic measurement. 3 Parallell framework contracts | Other | All projects | Open | No | Service | n/a | 2019-04-29 | 2019-05-29 | 2019-07-01 | Unavailable |  | Green - information certain (within 3 months)
15015 | Framework contract for removing graffiti | Framework contract for removing graffiti on plank | Other | All projects | Open | No | Service | n/a | 2019-05-13 | 2019-06-17 | 2019-08-01 | Unavailable |  | Green - information certain (within 3 months)
15016 | Framework contract- postal services | Framework contract- postal services | Other | All projects | Open | No | Service | n/a | 2019-05-13 | 2019-06-17 | 2019-08-01 | Unavailable |  | Green - information certain (within 3 months)
4771 | Safety engineering installations | The contract includes design and installation (including operation and maintenance) of temporary safety engineering systems for the expansion of the underground train system to Barkarby and Arenastaden. This consists of radio communication, data networks, systems for monitoring of personnel and equipment underground, and emergency evacuation alarms. These systems shall be in operation from the start of tunnel blasting, until the start of commercial train operations. At this time the contractor is to remove all equipment they have installed in line with the Clients orders. The contractor shall design and install the system for minimum reworking and/or replacement of equipment during the projects lifecycle. | Building and installation works |  | Open | No | Design & Build Contract | No | 2019-05-29 | 2019-09-11 | 2019-11-01 | 20-50 |  | Green - information certain (within 3 months)
7714 | Access tunnel Hammarby kanal, Hammarby fabriksväg | The contract comprises rock shafts for Access tunnel and creating establishment areas at ststion Hammarby sjöstad. | Rock excavation and civil works | Södermalm | Negotiated | Yes 9.4.3 | Build only contract | finished | 2019-05-29 | 2019-11-18 | 2020-02-01 | 50-100 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan and environmental ruling - estimated June 2019
15011 | Accommodation modules | Removable modules for residential purposes. The modules are set for non-permanent use. The company will disassembled the modules and send them away, after the end of the rentalperiod. | Other | All projects | Open | No | Service | n/a | 2019-06-08 | 2019-09-01 | 2019-10-01 | 50-100 |  | Green - information certain (within 3 months) | Green - information certain (within 3 months)
7711 | Rail and service tunnel Kungsträdgården (Ktg) | The contract comprises rock shafts for rail tunnels and service on Blasieholmen. Concreting works and connecting earth works for ways up and entrances are also included. | Rock excavation and civil works | Södermalm | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | Ongoing | 2019-06-17 | 2019-12-31 | 2020-02-01 | 300-500 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan and environmental ruling - estimated June 2019 Qualification is restarted
2676 | Rectifier substation | Joint procurement for all expansion lines | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Jointly | Negotiated | Yes 9.1.1 | Design & Build Contract | 2019-05-07 | 2019-07-01 | 2020-01-08 | 2020 Q2 | 200-400 |  | Green - information certain (within 3 months) | Red - information uncertain
| Escalators for 4721 | Procurement of escalators for the stations att Barkarby will be done separately from the contract for 4721 |  | Barkarby |  |  | Combo | 2019-07-01 | 2019-08-01 | 2019-10-01 | 2019-11-01 | 50-100 |  | Yellow- relativly certain information
15017 | inspection organization | inspection organization | Other | All projects | Open | No | Service | n/a | 2019-08-12 | 2019-09-20 | 2020-01-13 | 20-50 |  | Green - information certain (within 3 months)
7715 | Civil works Sofia | The contract comprises a rock shaft for rail tunnel and station areas. Concreting works and connecting earth works for ways up and entrances are also included. The greatest depth of the facility is at the passage under Saltsjön. The new facility connects to the existing station Kungsträdgården. | Rock excavation and civil works | Södermalm | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2019-08-15 | 2019-12-02 | 2020-08-28 | 2020-12-01 | 500-1000 |  | Green - information certain (within 3 months) |  | Railway plan and environmental ruling - estimated June 2019
8716 | Civil worksNacka | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2019-10-01 | 2020-01-01 | 2020-09-30 | 2021 Q1 | 300-500 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
3716 | Access tunnel Arenastaden | The assignment includes construction of a Access tunnel and preparation of an establishment area | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.3 | Build only contract | 2019-09-15 | 2019-11-15 | 2020-03-15 | 2020-05-01 | 50-100 |  | Red - information uncertain | Red - information uncertain | Railwayplan - estimated March 2020
9715 | Civil works Gullmarsplan | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2019-10-01 | 2019-12-13 | 2020-Q3 | 2020 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
4721 | Building and installation, Järfälla tunnel and stations | Including framework completion Installations (building incl. telecom) | Building and installation works | Barkarby | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2019-09-01 | 2019-21-01 | 2020 Q3 | 2020 Q4 | 500-1,000 |  | Yellow- relativly certain information | Red - information uncertain
5712 | Access tunnel (excl. concrete tunnel) Örbyleden | Mainly including preparatory works, sheeting, earth and rock excavation, including injection and reinforcement works. | Rock excavation and civil works | Depot | Negotiated | Yes 9.4.3 | Build only contract | 2019 Q4 | 2020 Q1 | 2020 Q3 | 2020 Q4 | 20-50 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated summer 2020
5711 | Kvicksundsvägen, Concrete tunnel | Construction of a concrete tunnel, including preparatory works, sheeting, earth and rock excavation, grouting and reinforcement works. Pipe rerouting. | Rock excavation and civil works | Depot | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q1 | 2020 Q2 | 2020 Q3 | 2020 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated summer 2020
5713 | Main tunnel, connecting tracks and sidings hall | Excavation of main cavern and connecting tunnels. | Rock excavation and civil works | Depot | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q1 | 2020 Q2 | 2020 Q3 | 2020 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated summer 2020
9712 | Civil works Sockenplan , stage 2 / Slakthusområdet | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q1 | 2020 Q2 | 2020 Q4 | 2021 Q1 | 300-500 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated June 2019
8714 | Civil works Sickla | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q1-Q2 | 2020 Q3 | 2021 Q1 | 2021 Q2 | 300-500 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated June 2019
8715 | Civil works Järla | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q1-Q2 | 2020 Q3 | 2021 Q1 | 2021 Q2 | 300-500 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated June 2019
4743 | Track | BEST Track (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Negotiated | Yes 9.1.1 | Build only contract | 2020 Q2 | 2020 Q3 | 2021 Q2 | 2021 Q3 | Unavailable |  | Red - information uncertain | Red - information uncertain
7716 | Civil works Hammarby kanal | The contract comprises a rock shaft for rail tunnel and station areas at Sofia and Hammarby kanal. Concreting works and connecting earth works for ways up and entrances are also included. | Rock excavation and civil works | Södermalm | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q2 | 2020 Q3 | 2021 Q2 | 2021 Q3 | 500-1000 |  | Red - information uncertain | Red - information uncertain | Railway plan and environmental ruling - estimated June 2019
| Building and installation works Stations | Nacka, Sickla, Järla and Nacka C. Framework completions and installations for ticket halls, platforms, etc. | Building and installation works | Nacka | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q3 | 2020 Q3 | 2021 Q1 | 2021 Q4 | 500-1,000 |  | Red - information uncertain | Red - information uncertain | May be diveded into more contracts
| Building and installation works 2 stations | The contract comprises framework completions and installations for entrances, ticket halls, mezzanines, platforms, technical plan, service tunnel, ventilation shaft, fire shaft, etc. at the stations Sofia and Hammarbykanal. | Building and installation works | Södermalm | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2022 Q4 | 500-1 000 |  | Red - information uncertain | Red - information uncertain | May be divided inte more contracts Railway plan - estimated June 2019
| Building and installation works 3 stations | Southern suburbs, Gullmarsplan, Slakthuset and connection Sockenplan. Framework completions and installations for ticket halls, platforms, etc. | Building and installation works | Söderort | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q3 | 2020 Q4 | 2021 Q1 | § | 500-1,000 |  | Red - information uncertain | Red - information uncertain | May be divided into more contrcts
3711 | Rock excavation and civil works Hagastaden, including building and installation | The contracts comprise rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for Hagastaden station and connecting tunnels to Odenplan and Hagalund. Earth and foundation works for ticket halls. The contracts comprise, among other things, framework completions with light walls, wall panels, forging, glass partitions, false ceiling, floor and other surface layers. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/telecom, lifts, escalators for complete station. | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2019-11-01 | 2020-02-01 | 2020-09-01 | Q2 2021 | >1000 |  | Red - information uncertain | Red - information uncertain | Railwayplan - estimated March 2020
3723 | Building and installation works Arenastaden | The contracts comprise, among other things, framework completions with light walls, wall panels, forging, glass partitions, false ceiling, floor and other surface layers. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/telecom, lifts, escalators for complete station. | Building and installation works | Arenastaden | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2020 Q4 | 2021 Q1 | 2021 Q3 | 2022 Q3 | 300-500 |  | Red - information uncertain | Red - information uncertain | Possible combined procurement for FUT id nr 3722 and 3723. Railwayplan - estimated March 2020
3742 | BEST assembly (Track-, Electrical-, Signal- and Telecommunication works) | The contract comprises assembly works for new rail installation. Rail and switch assembly, third-rail installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Arenastaden | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q1 | 2021 Q1 | 2022 Q1 | 2023 Q1 | Unavailable |  | Red - information uncertain | Red - information uncertain
26711 | Track, walking path, Thrid rail 750V. | Track work, troughs, Thrid rail 750 V . For Kungsträdgården - Hammarby Kanal and Sofia- Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q1 | 2021 Q1 | 2021 Q3 | 2021 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
26712 | Track, walking path, Thrid rail 750V. | Track work, troughs, Thrid rail 750 V . For Hammarby Kanal - Nacka | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q1 | 2021 Q1 | 2021 Q3 | 2021 Q4 | 300-500 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated June 2019
3722 | Building and installation works Hagalund | The contracts comprise, among other things, framework completions with light walls, wall panels, forging, glass partitions, false ceiling, floor and other surface layers. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/telecom, lifts, escalators for complete station. | Building and installation works | Arenastaden | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2021 Q1 | 2021 Q2 | 2022 Q1 | 2022 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain | Possible combined procurement for FUT id nr 3722 and 3723. Railwayplan - estimated March 2020
2672 | Electricity 400V, Telecom | Electricity 400V, Telecom. For Kungsträdgården - Nacka and Sofia - Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q1 | 2021 Q2 | 2021 Q4 | 2022 Q1 | 50-100 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
2674 | Mouting ducting and cabling | Mouting ducting och cabling. For Kungsträdgården - Nacka and Sofia- Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q3 | 2021 Q3 | 2022 Q1 | 2022 Q2 | 50-100 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
5726 | Interior fittings and installations in underground tunnel and cavern | Installations in work and service tunnel, connecting track and storage hall below ground. (Sprinklers, lighting, etc.) | Building and installation works | Depot | Negotiated | Yes | Build only contract | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 50-100 |  | Red - information uncertain | Red - information uncertain
26731 | Signal | Signalinstallation for Kungsträdgården - Nacka and Sofia - Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Negotiated | Yes 9.1.1 | Build only contract | 2021 Q3 | 2021 Q4 | 2022 Q2 | 2022 Q3 | 100-300 |  | Red - information uncertain | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
4742 | Electricity 400 volt | BEST Electricity & Telecom (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Negotiated | Yes 9.1.1 | Build only contract | 2021-Q3 | 2021-Q4 | 2022-Q2 | 2022-Q3 | Unavailable |  | Red - information uncertain | Red - information uncertain
4744 | Signal | BEST Signal (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Negotiated | Yes 9.1.1 | Build only contract | 2022 Q1 | 2022 Q2 | 2022 Q4 | 2023 Q1 | Unavailable |  | Red - information uncertain | Red - information uncertain
9713 | Civil works Sockenplan stage 3 | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | 2022 Q1 | 2022 Q2 | 2023 Q1 | 2023 Q4 | 300-500 |  | Red - information uncertain |  | Railway plan, and Environmental ruling - estimated June 2019
5721 | Expanded sidings shed | Existing buildning above ground to be expanded with a garaging point for 4 trains. | Building and installation works | Depot | Negotiated | Yes | Design & Build Contract | Data will be completed | Data will be completed | Data will be completed | Data will be completed | 20-50 |  | Red - information uncertain | Red - information uncertain
5722 | Extension of existing building | Extension of existing cleaning shed | Building and installation works | Depot | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Design & Build Contract | Data will be completed | Data will be completed | Data will be completed | Data will be completed | 20-50 |  | Red - information uncertain | Red - information uncertain
5723 | Workshop area | A new workshop (C30), approximately 80x10 metres shall be built. | Building and installation works | Depot | Negotiated | Yes | Build only contract | Data will be completed | Data will be completed | Data will be completed | Data will be completed | 50-100 |  | Red - information uncertain | Red - information uncertain
5724 | New cleaning and siding shed | Construction of a new building with a garaging point for 8 trains. | Building and installation works | Depot | Negotiated | Yes | Design & Build Contract | Data will be completed | Data will be completed | Data will be completed | Data will be completed | 50-100 |  | Red - information uncertain | Red - information uncertain
5740 | BEST (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Depot | Negotiated | Yes 9.1.1 | Build only contract | Data will be completed | Data will be completed | Data will be completed | Data will be completed | 100-300 |  | Red - information uncertain | Red - information uncertain
15008 | IT systems for IT support for environmental influences | The assignment is to develop a new IT system for environmental databases. The environmental database shall handle reporting and review of larger amounts of measurement data from all of the subway projects. The database should clearly illustrate the location of the measurement objects in a map function and be an easy-to-use tool for the daily work of monitoring and reporting to regulatory. | Other | All projects | Negotiated | No | Service | finished | Ongoing procurement | 2019-05-21 | 2019-06-01 | 5-20 |  | Green - information certain (within 3 months) | Green - information certain (within 3 months)
15009 | Organisation for measuring environmental influences (noise and vibrations etc.) - Contract area NORTH | Measurements and monitoring of vibrations, cracks/breakages, incl. fixed noise meters etc. (surveyors, management and rentals of instruments) for the tunnel extension projeckts of: Akalla-Barkarby, Odenplan - Arenastaden, samt Depå. | Other | All projects | Open | No | Service | n/a | Ongoing procurement | Ongoing evaluation | 2019-06 | 20-50 |  | Green - information certain (within 3 months)
15010 | Organisation for measuring environmental influences (noise and vibrations etc.) - Contract area SOUTH | Measurements and monitoring of vibrations, cracks/breakages, incl. fixed noise meters etc. (surveyors, management and rentals of instruments) for the tunnel extension projeckts of: Kungsträdgården-Luma samt Sofia-Skanstull Marina, Skanstull Marina - Sockenplan, samt Sickla (Luma)-Nacka C. | Other | All projects | Open | No | Service | n/a | Ongoing procurement | Ongoing evaluation | 2019-06 | 20-50 |  | Green - information certain (within 3 months)
15013 | Mass handling contract | Mass handling | Rock excavation and civil works | Nacka-southern suburbs | Negotiated | No | Build only contract | n/a | Ongoing procurement | Ongoing evaluation | 2019-06-01 | Unavailable |  | Green - information certain (within 3 months) | Red - information uncertain
4713 | Main tunnel, Järfälla tunnel | The contract comprise mainly rock excavation works, rock reinforcement and grouting for tunnels, caverns, shafts. Concrete and steel structural works and concrete framework for among other underground stations Barkarby and Barkarbystaden. Sheet piling, earth- and foundation works for entrances and ventilation shafts. Design responsibility for concrete and steel works, temporary geotecknical support structures and temporary installations for construction period that shall remain upon completion. | Rock excavation and civil works | Barkarby | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | finished | Ongoing procurement | 2019-08-30 | 2019-10-01 | > 1 000 |  | Green - information certain (within 3 months) | Red - information uncertain | Environmental permit - approved. Railwayplan - approved.
7713 | Access tunnel Londonviadukten | The assignment includes construction of an Access tunnel and preparation of an establishment area Station Sofia | Rock excavation and civil works | Södermalm | Negotiated | Yes 9.4.3 | Build only contract | Completed | Ongoing procurement | 2019-06-14 | 2019-06-01 | 100-300 | Yellow- relativly certain information | Green - information certain (within 3 months) |  | Railway plan and environmental ruling - estimated June 2019
87131 | Access tunnel Sickla, Värmdövägen | The assignment includes construction of an Access tunnel and preparation of an establishment area | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.3 | Build only contract | finished | Ongoing procurement | 2019-08-30 | 2019-10-15 | 100-300 | Red - information uncertain | Green - information certain (within 3 months) |  | Possible combined procurement for FUT id nr 87131 and 87132 Railway plan, and Environmental ruling - estimated June 2019
87132 | Access tunnels Järla östra | The assignment includes construction of an Access tunnel and preparation of an establishment area | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.3 | Build only contract | finished | Ongoing procurement | 2019-08-30 | 2019-10-15 | 100-300 | Red - information uncertain | Green - information certain (within 3 months) |  | Possible combined procurement for FUT id nr 87131 and 87132 Railway plan, and Environmental ruling - estimated June 2019
87133 | Access tunnel Nacka C, Skönviksvägen | The assignment includes construction of an Access tunnel and preparation of an establishment area | Rock excavation and civil works | Nacka | Negotiated | Yes 9.4.3 | Build only contract | finished | Ongoing procurement | 2019-07-08 | 2019-09-15 | 100-300 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
9711 | Sockenplan stage 1 | Civil works; preparing construction site area, sheet piling, excavation, rock tunnel, cut and cover tunnel | Civil works incl rock excavation | Söderort | Negotiated | Yes 9.4.3 | Build only contract | finished | Ongoing procurement | 2019-09-20 | 2019-11-01 | 100-300 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
9714 | Access tunnel, Gullmarsplan / Sundstabacken | The assignment includes construction of a Access tunnel and preparation of an establishment area. | Rock excavation and civil works | Söderort | Negotiated | Yes 9.4.3 | Build only contract | finished | Ongoing procurement | 2019-09-06 | 2019-10-16 | 100-300 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan, and Environmental ruling - estimated June 2019
3714 | Access tunnel Hagastaden | The assignment includes construction of a Access tunnel and preparation of an establishment area | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.3 | Build only contract | finished | Procurement in progress | 2019-10-20 | 2019-12-15 | 50-100 |  | Green - information certain (within 3 months) | Red - information uncertain | Railwayplan - estimated March 2020
3715 | Access tunnel Södra Hagalund | The assignment includes construction of a Access tunnel and preparation of an establishment area | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.3 | Build only contract | finished | Procurement in progress | 2019-09-02 | 2019-10-15 | 50-100 |  | Green - information certain (within 3 months) | Red - information uncertain | Railwayplan - estimated March 2020
3712 | Rock excavation and civil works Södra Hagalund | The contracts comprise rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for Hagalund station and connecting tunnels to Hagastaden and Arenastaden. Earth and foundation works for ticket halls. | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | Q1 2020 | Q2 2020 | Q3 2020 | Q2 2021 | 500-1,000 |  | Red - information uncertain | Red - information uncertain | Possible combined procurement for FUT id nr 3712 and 3713. Railwayplan - estimated March 2020
3713 | Rock excavation and civil works Arenastaden | The contracts comprise rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for complete station Arenastaden and connecting tunnels to Hagalund. Earth and foundation works for ticket halls. | Rock excavation and civil works | Arenastaden | Negotiated | Yes 9.4.1 – 9.4.9 and 9.4.99 | Build only contract | Q1 2020 | Q2 2020 | Q3 2020 | Q2 2021 | 300-500 |  | Red - information uncertain | Red - information uncertain | Possible combined procurement for FUT id nr 3712 and 3713. Railwayplan - estimated March 2020

## template
Uppdrag | Projekt | Förfarande | Transq | Entreprenadform | Kostnad | Upphandlare | Sannolikhet
Framework agreement | Barkarby | Simplified procedure | Yes 9.1.0 9.4.0 | Build only contract | 0-5 | Anders Karnestrand | Green - information certain (within 3 months)
Preparatory work | Arenastaden | Open | No | Design & Build Contract | 5-20 | Cecilia Tennfors | Red - information uncertain
Yellow- relativly certain information
Access tunnel works | Depå | Negotiated |  | Combo | 20-50 | Pia Lindberg-Nedby | Data not available
Rock excavation and civil works | Nacka |  |  | Service | 50-100 | Peter Malmsten
Building and installation works | Söderort |  |  |  | 100-300
Installation | Södermalm |  |  |  | 300-500
BEST (Track-, Electrical-, Signal- and Telecommunication works) | All projects |  |  |  | 500-1 000
Other |  |  |  |  | > 1 000
Combination |  |  |  |  | Data missing